## Control Assessment
Control ID | Control Name | Related Risk | Control Objective | Current State | Assessment Result | Control Type | Evidence Reviewed | Recommended Improvement | Owner | Priority | Status | Framework Reference
C-01 | Privileged Access MFA | R-02 | Require stronger authentication for privileged AWS access. | MFA is enabled for admin users, but enforcement for all privileged roles is not fully documented. | Partially Effective | Preventive | IAM settings, MFA configuration screenshots | Document enforcement standard and validate MFA coverage for all privileged access paths. | Cloud Security | High | In Progress | SOC 2 CC6; NIST PR.AA; CIS 6
C-02 | Least Privilege IAM Review | R-01, R-02 | Limit AWS and production access to only what users and roles need. | IAM roles exist, but permissions have grown over time and some roles appear broader than necessary. | Needs Improvement | Preventive | IAM policies, role permission review | Perform role-by-role review, remove unnecessary permissions, and define approval requirements for elevated access. | Cloud Security | High | Open | SOC 2 CC6; NIST PR.AA; CIS 5/6
C-03 | Cloud Configuration Monitoring | R-03 | Detect insecure changes to production AWS resources before they create exposure. | Logging and configuration visibility exist, but there is no consistent review process for high-risk misconfigurations. | Partially Effective | Detective | CloudTrail logs, config review notes | Define review cadence for critical cloud settings and alert on high-risk configuration drift. | Cloud Ops | High | In Progress | SOC 2 CC7, CC8; NIST PR.PS; CIS 4/12
C-04 | Centralized Logging and Alert Review | R-04 | Capture and review security-relevant activity across AWS and production systems. | CloudTrail is enabled and some alerts exist, but alert tuning and analyst review are inconsistent. | Partially Effective | Detective | CloudTrail config, alert rules, sample log output | Tune alerts, assign review ownership, and retain evidence of regular monitoring activity. | Security Operations | High | In Progress | SOC 2 CC7; NIST DE.CM; CIS 8
C-05 | Joiner/Mover/Leaver Access Process | R-05 | Ensure user access is provisioned, changed, and removed in a timely manner. | Access requests are handled, but offboarding and role changes are not consistently tracked end to end. | Needs Improvement | Administrative | Ticket samples, onboarding/offboarding workflow | Formalize workflow between HR and IT and require evidence for provisioning and deprovisioning completion. | IT / HR | High | Open | SOC 2 CC6; NIST PR.AA; CIS 5
C-06 | Quarterly Access Reviews | R-06 | Confirm access remains appropriate for users with production or sensitive access. | Managers review access informally, but approvals and exceptions are not consistently retained. | Needs Improvement | Detective | Access review samples, manager approvals | Standardize quarterly review templates and store evidence of completion and remediation. | IT Manager | Medium | Open | SOC 2 CC6; NIST GV.RR, PR.AA; CIS 6
C-07 | Vendor Security Review | R-07 | Evaluate third parties that store data or support critical services before onboarding and during renewal. | Some vendor checks are performed, but there is no standard questionnaire, scoring method, or review cadence. | Needs Improvement | Administrative | Vendor list, contracts, sample questionnaire | Create a standard vendor review workflow with risk tiering and periodic reassessment. | GRC / Procurement | Medium | Open | SOC 2 CC9; NIST GV.SC; CIS 15
C-08 | Backup Restore Testing | R-08 | Verify backups can be restored within expected recovery needs. | Backups are configured, but restore testing is not performed on a defined schedule. | Needs Improvement | Corrective | Backup configuration, test records | Schedule and document periodic restore tests and compare results to recovery expectations. | IT Ops | High | Open | SOC 2 A1; NIST RC.RP; CIS 11