## SOC2_Gap_Analysis
Criteria Area | Control Objective | Current State | Gap Identified | Risk Level | Priority | Owner | Evidence Reviewed | Recommended Action | Target Date | Status | Control Reference
CC1.1 Control Environment | Security roles and responsibilities are defined | Roles exist but not consistently documented across teams | Governance documentation is incomplete and not centrally maintained | Medium | Medium | Security Leadership | Org charts, onboarding docs | Centralize and document roles and responsibilities in a formal governance document | 2026-06-01 | Open | SOC2 CC1.1; NIST PR.AA; CIS 5
CC2.1 Communication | Internal security policies are communicated | Policies exist but distribution is inconsistent | No formal communication or acknowledgment process | Medium | Medium | GRC | Policy docs, employee records | Implement policy distribution and acknowledgment tracking | 2026-06-15 | Open | SOC2 CC2.1; CIS 14
CC3.2 Risk Assessment | Risks are identified and assessed regularly | Risk register exists but not reviewed regularly | No formal recurring review cadence | Medium | High | GRC | Risk register spreadsheet | Establish quarterly risk review meetings and updates | 2026-05-15 | Open | SOC2 CC3.2; NIST ID.RA
CC6.1 Logical Access | Access to systems is restricted by role | AWS IAM roles exist, MFA enabled for admins | Access reviews not consistently documented | High | High | Cloud Security | IAM configs, MFA logs | Formalize quarterly access reviews and retain evidence | 2026-04-30 | In Progress | SOC2 CC6; NIST PR.AA; CIS 6
CC6.7 Monitoring | Security events are logged and monitored | CloudTrail enabled but alerts are basic | Alert coverage and review cadence are limited | High | High | Security Operations | CloudTrail logs, alert configs | Enhance alerting rules and define monitoring review process | 2026-05-01 | In Progress | SOC2 CC7; NIST DE.CM; CIS 8
CC7.2 Vendor Oversight | Third parties are evaluated for risk | Some vendor reviews exist | No standardized vendor risk process | Medium | Medium | GRC | Vendor list, contracts | Implement vendor risk review workflow and documentation | 2026-06-10 | Open | SOC2 CC7.2; CIS 15
CC8.1 Incident Response | Security incidents are managed through a defined process | Ad hoc incident response approach | No formal IR plan or testing | High | High | Security Operations | Incident tickets, past responses | Develop and test formal incident response plan | 2026-04-20 | Open | SOC2 CC8; NIST RS; CIS 17
A1 Availability | Systems are backed up and recoverable | Backups exist but not regularly tested | Recovery testing not documented | High | High | Cloud Engineering | Backup configs, logs | Implement periodic backup restoration testing | 2026-05-05 | Open | SOC2 A1; NIST RC; CIS 11