## AI_Risk_Register
Risk ID | AI Use Case | Risk Description | Likelihood | Impact | Score | Owner | Mitigation Strategy | Status | Framework Reference
AI-01 | LLM-assisted customer support | Model may expose sensitive customer data through prompts or responses | 3 | 5 | 15 | Security / AI Governance | Implement prompt filtering, data masking, and access controls | Open | NIST AI RMF; SOC2 CC6; CIS 3
AI-02 | Internal AI coding assistant | Generated code may introduce insecure patterns or vulnerabilities | 4 | 4 | 16 | Engineering | Require code review and secure coding validation | Open | NIST AI RMF; CIS 16
AI-03 | AI analytics on customer data | Improper data handling could violate privacy or compliance requirements | 3 | 5 | 15 | Data / GRC | Restrict datasets, enforce anonymization and access control | Open | SOC2 CC3; NIST PR.DS
AI-04 | Third-party AI API usage | Vendor AI services may store or reuse submitted data | 3 | 4 | 12 | GRC / Procurement | Review vendor terms, restrict sensitive data usage | Open | SOC2 CC9; CIS 15
AI-05 | Automated decision making | AI outputs may be inaccurate or biased impacting business decisions | 3 | 4 | 12 | Business / Risk | Require human validation and monitoring | Open | NIST AI RMF